## Gantchart
GANTT CHART Mini Project | [6 empty] | Smartsheet Tip ➜ | [5 empty] | A Gantt chart's visual timeline allows you to see details about each task as well as project dependencies.
PROJECT TITLE Online Survey System | [6 empty] | DEPARTMENT NAME | [6 empty] | IT
PROJECT GUIDE Prof. Yaminee Patil | [6 empty] | DATE | [6 empty] | 2018-03-12
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION(Weeks) | PERCENTAGE OF TASK COMPLETE | PHASE ONE | [24 empty] | PHASE TWO
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception and Initiation
WEEK 1 | Creating Login Page and Registration page | LAKSHIT PATIL,SHREYASH GHUTE | 9/15/21 | 9/28/21 | 2 | 100% | bar: WEEK 1 F to WEEK 2 F
WEEK 2 | Product Page creation and button connections | LAKSHIT PATIL,SHREYASH GHUTE | 9/20/21 | 9/26/21 | 1 | 100% | bar: WEEK 2 W to WEEK 2 F
WEEK 3 | Designing User and Admin Interface | LAKSHIT PATIL,SHREYASH GHUTE | 2021-06-10 | 2021-11-10 | 1 | 100% | bar: WEEK 2 W to WEEK 3 W
WEEK 4 | Presentation I | LAKSHIT PATIL,SHREYASH GHUTE | 2021-12-10 | 10-18-21 | 1 | 100% | bar: WEEK 2 W to WEEK 3 R
2 | Project Design and Implementation
WEEK 5 | Designing login, Registration and product page | LAKSHIT PATIL,SHREYASH GHUTE | 10/14/21 | 10/22/21 | 1 | 100% | bar: WEEK 2 W to WEEK 3 R
WEEK 6 | Creating User and Admin Display page | LAKSHIT PATIL,SHREYASH GHUTE | 10/23/21 | 10/30/21 | 1 | 100% | bar: WEEK 2 W to WEEK 2 F; WEEK 4 M to WEEK 4 R
WEEK 7 | Database connectivity with login and registration page | LAKSHIT PATIL,SHREYASH GHUTE | 2021-07-11 | 2021-12-11 | 1 | 100% | bar: WEEK 2 W to WEEK 2 F; WEEK 4 F to WEEK 5 F
WEEK 8 | Results and Report Writing | LAKSHIT PATIL,SHREYASH GHUTE | 11/13/21 | 11/20/21 | 1 | 100% | bar: WEEK 2 W to WEEK 2 F; WEEK 6 M to WEEK 7 F
WEEK 9 | Presentation II | LAKSHIT PATIL,SHREYASH GHUTE | 11/22/21 | 2021-01-12 | 1 | 100% | bar: WEEK 2 W to WEEK 2 F; WEEK 8 M to WEEK 9 F