## Gantchart
GANTT CHART Mini Project | [6 empty] | Smartsheet Tip ➜ | [5 empty] | A Gantt chart's visual timeline allows you to see details about each task as well as project dependencies.
PROJECT TITLE |  | Student Admission Management System |  |  |  |  | DEPARTMENT NAME | [6 empty] | Information Technology
PROJECT GUIDE |  | Sonal Jain |  |  |  |  | DATE | [6 empty] | 2018-03-12
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION(Weeks) | PERCENTAGE OF TASK COMPLETE | PHASE ONE | [24 empty] | PHASE TWO
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception and Initiation
WEEK 1 | Designing Login and Registration Page for Student and Admin Designing Student Panel with Logout Button Designing Admin Panel | Chirag Padyal,Anuj Kunder, Jaykumar Nayi, Vishal Bangar | 2021-09-12 | 2021-09-22 | 2 | 100% | bar: WEEK 1 F to WEEK 2 F
WEEK 2 | Qualification Form Personal Detail form Branch Detail Form | Chirag Padyal, Anuj Kunder | 2021-09-19 | 2021-09-26 | 1 | 100% | bar: WEEK 2 W to WEEK 2 F
WEEK 3 | Student / Admin Login and Registration JDBC connection | Vishal Bangaar, Jaykumar Nayi | 2021-10-06 | 2021-10-14 | 1 | 100% | bar: WEEK 2 W to WEEK 3 W
WEEK 4 | Presentation I | Chirag Padyal, Jaykumar Nayi | 2021-10-12 | 2021-10-19 | 1 | 100% | bar: WEEK 2 W to WEEK 3 R
2 | Project Design and Implementation
WEEK 5 | Student Qualification, Personal Detail and Branch Detail Form Backend Connection and Document Upload. | Chirag Padyal, Anuj Kunder | 2021-10-14 | 2021-10-23 | 1 | 100% | bar: WEEK 2 W to WEEK 3 R
WEEK 6 | Admin Panel Tabular Data From All Student Table. | Chirag Padyal, Anuj Kunder | 2021-10-21 | 2021-10-30 | 1 | 100% | bar: WEEK 2 W to WEEK 2 F; WEEK 4 M to WEEK 4 R
WEEK 7 | Input Limit and Form Button Disable | Vishal Bangar , Jaykumar Nayi | 2021-11-07 | 2021-11-10 | 1 | 100% | bar: WEEK 2 W to WEEK 2 F; WEEK 4 F to WEEK 5 F
WEEK 8 | Auto Qualification based on Mark-Sheet | Chirag Padyal, Jaykumar Nayi | 2021-11-11 | 2021-11-20 | 1 | 100% | bar: WEEK 2 W to WEEK 2 F; WEEK 6 M to WEEK 7 F
WEEK 9 | Presentation II | Chirag Padyal,Anuj Kunder, Jaykumar Nayi, Vishal Bangar | 2021-11-20 | 2021-12-02 | 1 | 100% | bar: WEEK 2 W to WEEK 2 F; WEEK 8 M to WEEK 9 F