## Gantchart
GANTT CHART Mini Project | [6 empty] | Smartsheet Tip ➜ | [5 empty] | A Gantt chart's visual timeline allows you to see details about each task as well as project dependencies.
ONLINE BANKING SYSTEM | [6 empty] | DEPARTMENT NAME | [6 empty] | INFORMATION TECHNOLOGY
GUIDE: NEHA DESHMUKH | [6 empty] | DATE | [6 empty] | 2018-03-12
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION(Weeks) | PERCENTAGE OF TASK COMPLETE | PHASE ONE | [24 empty] | PHASE TWO
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception and Initiation
WEEK 1 | Group formation and Topic finalization. Identifying the scope and objectives of the Mini Project | Sakshi Ahire,Sakshi Gaikwad,Disha Panchal,Soham Bolla | 2021-09-17 | 2021-09-19 | 2 | 100% | bar: WEEK 1 F to WEEK 2 F
WEEK 2 | Identifying the technology stack and functionalities of the Mini Project | Soham Bolla,Sakshi Ahire | 2021-09-22 | 2021-09-22 | 1 | 100% | bar: WEEK 2 W to WEEK 2 F
WEEK 3 | Discussing the project topic with the help of paper prototype. | Sakshi Gaikwad,Disha panchal | 17--09-2021 | 2021-09-20 | 1 | 100% | bar: WEEK 2 W to WEEK 3 W
WEEK 4 | Presentation I | Sakshi Gaikwad,Sakshi Ahire | 2021-09-22 | 2021-10-13 | 1 | 100% | bar: WEEK 2 W to WEEK 3 R
2 | Project Design and Implementation
WEEK 5 | Designing the Graphical User Interface(GUI) | Sakshi Ahire | 2021-10-20 | 2021-11-25 | 1 | 100% | bar: WEEK 2 W to WEEK 3 R
WEEK 6 | Database Design | Sakshi Ahire, Soham Bolla | 10-20-2021 | 2021-11-25 | 1 | 100% | bar: WEEK 2 W to WEEK 2 F; WEEK 4 M to WEEK 4 R
WEEK 7 | Database Connectivity with front end | Sakshi Ahire,Soham Bolla,Sakshi Gaikwad,Disha panchal | 2021-11-20 | 2021-11-28 | 1 | 100% | bar: WEEK 2 W to WEEK 2 F; WEEK 4 F to WEEK 5 F
WEEK 8 | Results and Report Writing | Sakshi Gaikwad,Disha panchal,Sakshi Ahire | 2021-11-23 | 2021-11-30 | 1 | 100% | bar: WEEK 2 W to WEEK 2 F; WEEK 6 M to WEEK 7 F
WEEK 9 | Presentation II | Sakshi Gaikwad,Disha panchal | 2021-11-26 | 409772 | 1 | 100% | bar: WEEK 2 W to WEEK 2 F; WEEK 8 M to WEEK 9 F