## Gantchart
GANTT CHART Mini Project | [6 empty] | Smartsheet Tip ➜ | [5 empty] | A Gantt chart's visual timeline allows you to see details about each task as well as project dependencies.
PROJECT TITLE : BEAUTY PARLOUR BILLING SYSTEM | [6 empty] | DEPARTMENT NAME : INFORMATION TECHNOLOGY
PROJECT GUIDE : PROF. NAHID SHAIKH | [6 empty] | DATE | [6 empty] | 30/11/21
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION(Weeks) | PERCENTAGE OF TASK COMPLETE | PHASE ONE | [24 empty] | PHASE TWO
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9
[7 empty] | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F
1 | Project Conception and Initiation
WEEK 1 | Group formation and Topic finalization. Identifying the scope and objectives of the Mini Project | SHREYA MAHAJAN | 20/8/21 | 21/8/21 | 1 | 100% | bar: WEEK 1 F to WEEK 2 F
WEEK 2 | Identifying the technology stack and functionalities of the Mini Project | SHREYA MAHAJAN | 2021-01-09 | 2021-08-09 | 1 | 100% | bar: WEEK 2 W to WEEK 2 F
WEEK 3 | Discussing the project topic with the help of paper prototype. | SHREYA MAHAJAN, SANIYA DUTTA, ANISH BHOSALE | 2021-09-09 | 16/9/21 | 1 | 100% | bar: WEEK 2 W to WEEK 3 W
WEEK 4 | Presentation I | SHREYA MAHAJAN, SANIYA DUTTA, ANISH BHOSALE | 18/9/21 | 22/9/21 | 1 | 100% | bar: WEEK 2 W to WEEK 3 T
2 | Project Design and Implementation
WEEK 5 | Designing the Graphical User Interface(GUI) | SHREYA MAHAJAN | 24/9/21 | 2021-10-10 | 2 | 100% | bar: WEEK 2 W to WEEK 3 T
WEEK 6 | Database Design | SHREYA MAHAJAN | 2021-12-10 | 22/10/21 | 2 | 100% | bar: WEEK 2 W to WEEK 2 F; WEEK 4 M to WEEK 4 T
WEEK 7 | Database Connectivity with front end | SHREYA MAHAJAN, SANIYA DUTTA, ANISH BHOSALE | 23/10/21 | 2021-10-11 | 1 | 100% | bar: WEEK 2 W to WEEK 2 F; WEEK 4 F to WEEK 5 F
WEEK 8 | Results and Report Writing | SHREYA MAHAJAN, SANIYA DUTTA, ANISH BHOSALE | 22/11/21 | 24/11/21 | 1 | 100% | bar: WEEK 2 W to WEEK 2 F; WEEK 6 M to WEEK 7 F
WEEK 9 | Presentation II | SHREYA MAHAJAN, SANIYA DUTTA, ANISH BHOSALE | 30/11/21 | 30/11/21 | 1 | 100% | bar: WEEK 2 W to WEEK 2 F; WEEK 8 M to WEEK 9 F